## Introduction
This spreadsheet provides the framework to upgrade to the BTRS format. It can assist with the implementation of BTRS and how each bank must construct the BTRS file in order to produce harmonized formats and transaction code assignments – leading to more accurate reporting and lower development costs. This spreadsheet contains information that illustrates the standard specification of each Record Type. It also presents a sample project plan that can be used to develop your own plans to deliver BTRS. More information is available on the BTRS website at X9.ORG.
TAB | DESCRIPTION
Sample Project Plan | A guide that may help provide project governance around a technical project to upgrade from BAI2 to BTRS. It includes some considerations and elements that may not be applicable to every implementation.
Comparison Overview | A summary of all differences between BAI2 and BTRS
01 File Hdr | Details differences on the Record Level
02 Bank Hdr | Details differences on the Record Level
03 Bank Hdr | Details differences on the Record Level
16 Transaction Detail | Details differences on the Record Level
88 Continuation | Details differences on the Record Level
49 Account Trailer | Details differences on the Record Level
98 Bank Trailer | Details differences on the Record Level
99 File Trailer | Details differences on the Record Level
File Layout | A consolidated definition of all Record Types - provided in a spreadsheet format to easily copy into program code.
File Diagram | A Record Type definition in a visual format to better illustrate the components of the BTRS File Structure

## Sample Project Plan
Sample BTRS Implementation Project Plan
Date:
Task # | Task | Actions | Responsibility | Start Date | Target Date | Notes
1 | Analysis Phase
1.1 | BTRS Type Codes |  |  |  |  | Source: BTRS Spreadsheet (download from X9.ORG/BTRS)
1.1.1 | Identify all Applications that use BAI2 Codes |  |  |  |  | Determine which applications you are going to deliver BTRS from.
1.1.2 | Review the Retired Status, Summary and Detail Codes to determine mapping rules
1.1.3 | Review the New Status, Summary and Detail Codes to determine mapping rules
1.2 | BTRS User Guide |  |  |  |  | Source: BTRS User Guide (download from X9.ORG/BTRS)
1.2.1 | Review the "Version Control" to learn the Changes/Differences from BAI2
1.2.2 | Study the format of every Record Type to learn about the Standards, Placement, Rules and Best Practices.
1.3 | BTRS Comparison Overview |  |  |  |  | Source: BTRS Implementation Tools (download from X9.ORG/BTRS)
1.3.1 | Study the "Comparison Overview" tab within this Implementation Spreadsheet
1.3.2 | Study the differences and understand what has not changed within each Record Type.
1.4 | File Construction
1.4.1 | Study the "File Layout" & "File Diagram" tabs within this Implementation Spreadsheet
1.4.2 | Document the differences between code list for BAI2 and BTRS
1.4.3 | Document the differences between the records/layout for BAI2 and BTRS
1.5 | BTRS Delivery Design
1.5.1 | Determine how clients will receive a BTRS File (e.g., Online, Transmission, etc.) and if current BAI2 clients will remain or be offered to upgrade to BTRS.
1.5.2 | Determine impact to Implementation Procedures (onboarding)
1.5 | Filtering Preparation |  |  |  |  | Allow the continuation support of BAI2 and addition BTRS rules and mapping
1.5.1 | Understand the applications that will support BAI2
1.5.2 | Confirm the applications that will supports BTRS
2 | Requirements and Responsibilities |  | Technology
2.1 | Write User Agile Stories or Business Requirements |  | Business/Ops/Tech
2.1.1 | Continue to support BAI2
2.1.2 | Add ability to support BTRS
2.2 | Changes with the codes
2.2.1 | Determine the requirements, based on "BTRS Type Codes" Section 1.1
2.2.2 | Determine requirements for supporting both BAI2 and BTRS
2.3 | Changes with the records
2.3.1 | Determine the requirements, based on "BTRS User Guide" Section 1.2
2.3.2 | Determine the requirements, based on "BTRS Comparison Overview" Section 1.3
2.3.3 | Determine the requirements, based on "BTRS Comparison Overview" Section 1.3
2.4 | Client Communication
2.4.1 | Create client notification materials
2.4.2 | Prepare User Guides and Test File samples
2.5 | Change Readiness
2.5.1 | Determine changes to Sales Marketing Materials
2.5.2 | Determine changes to User Guides and Support Materials
2.5.3 | Determine Training Requirements
3 | Mapping
3.1 | Determine codes mapping for each application that will be supporting BTRS
3.2 | Applications that will be supporting BTRS will need to be re-coded to be able to produce BTRS. Alternatively they can make API calls to a standard package which can convert the internal objects to BTRS. If necessary these can be customized to the requirements.
3.3 | For applications that will continue with BAI2, implement a separate integration layer which will translate the BAI2 message to BTRS. This can either be hand-coded or by leveraging an integration vendor that supports BAI2 and BTRS.
4 | Testing Requirements
4.1 | Develop Test Cases for SIN, QA, and UAT
4.2 | Execute testing in each environment
4.3 | Complete End-to-End testing
4.4 | Remediate any defects and approve the testing phase
5 | Implementation
5.1 | Code Deployment
5.1.1 | Deploy program codes updates and conduct production validation
5.2 | Client Notification
5.2.1 | Publish appropriate client communication materials
5.3 | Implementation Procedures
5.3.1 | Deploy changes to BAI2/BTRS file setup procedures
5.3.2 | Provide training to Customer Support, Implementation and Sales
5.4 | Sales Materials
5.4.1 | Deploy Marketing Materials
5.4.2 | Deploy User Guides and Support Materials

## Comparison Overview
BTRS File Comparison to BAI2 - Overview
01 File Header |  | Begins the File
02 Group Header |  | Begins a Group
03 Account Identifier |  | Begins an Account
88 Continuation (Optional) |  | Reports additional information related to a specific Account
16 Transaction Detail (Optional) |  | Reports one specific Transaction
88 Continuation (Optional) |  | Reports additional information related to the specific Transaction
49 Account Trailer |  | Ends an Account
98 Group Trailer |  | Ends a Group
99 File Trailer |  | Ends the File
RECORD | FIELD | NOTES
01 and 02 | Military Time | For the purpose of Information Reporting, the general guideline is that 0000 indicates the beginning of the day and 2400 indicates the end of the day for the date indicated. However 0000 and 2400 both represent "midnight" in military format, the usage varying by organizations and applications. To avoid confusion and minimize conflicts with downstream applications, the best practice is to avoid 2400 and use a time range of 0000 - 2359.
01 | Version Number | Version Numbers 1 and 2 are reserved for BAI; Version Number 3 indicates BTRS.
02 | As-of Date Modifier | In BAI this field was Optional and used for reference only; in BTRS the field is Mandatory. The BAI field designator of 1 for "Interim Previous Day Data" has been retired and should not be used.
02 | Currency Code | In BAI this field was Optional and defaulted to USD. In BTRS the field is not used in Record 02. The Currency Code is only required at the account level in Record 03 since a single bank may report accounts with different currencies. In Record 02, no value is reported but the comma delimiter is still required to maintain the placeholder for the field.
03 | Currency Code | In BAI this field was Optional and defaulted to USD. In BTRS the field is Mandatory and based on international standard ISO 4217. The Currency Codes are the same as those used by SWIFT.
03 and 16 | Type Code | Many BAI2 Type Codes have been retired and are no longer used in BTRS; refer to the" X9.121 BTRS Version 3 Codes List" available on the X9.org site for a detailed list of viable BTRS Type Codes. Detail Type Codes are mapped to specific Summary Type Codes. If Summary Codes are included, they must correspond to the correct Detail Type Codes.
03 | Amount | In BAI this field was Optional, depending on the specific Type Code reported. Similarly in BTRS, this field is Conditional and dependent on the preceding Type Code. Including a Status or Summary Type Code with no Amount indicates that no amount is being reported (a special case that is different from reporting a zero amount).
03 and 16 | Funds Type | Funds Type "D" (Distributed Availability) is not used in BTRS. In BAI the Funds Type is Optional in Record 16. In BTRS the field is only optional for Detail Type Code 890, which is used for non-monetary information.
16 and 88 | Language | Characters must apply the UTF-8/Multi-byte format to allow for single byte and double byte character sets.
88 | (Next Field) | Refer to complete ANSI X9.121 documentation for detailed instructions on reporting Fedwire/CHIPS Wire Remittance Information and Batch Detail Invoice information in the BTRS 88 Record.

## 01 File Hdr
01 - FILE HEADER
FIELD NAME | REQUIRED or OPTIONAL | DESCRIPTION | BTRS vs. BAI
Record Code | Mandatory | 01 | N/C
Sender ID | Mandatory | Transmitter of the file; alphanumeric | N/C
Receiver ID | Mandatory | Next recipient of the file; alphanumeric | N/C
File Creation Date | Mandatory | Sender date; YYMMDD format | N/C
File Creation Time | Mandatory | Sender's local time; Military format (2400) | See Notes below
File ID Number | Mandatory | Unique number per file per date between sender and receiver | N/C
Physical Record Length | Optional | Number of characters in a physical record. Default is variable length records. | N/C
Block Size | Optional | Number of physical records in a block. Default is variable block size | N/C
Version Number | Mandatory | 3 | See Notes below
End of Record Delimiter | Mandatory | / | N/C
N/C = No change from BAI 2 format
| SAMPLE 01 RECORD: | 01,122099999,123456789,160621,0200,1,80,,3/
FIELD | NOTES
Military Time | For the purpose of Information Reporting, the general guideline is that 0000 indicates the beginning of the day and 2400 indicates the end of the day for the date indicated. However 0000 and 2400 both represent "midnight" in military format, the usage varying by organizations and applications. To avoid confusion and minimize conflicts with downstream applications, the best practice is to avoid 2400 and use a time range of 0000 - 2359.
Version Number | Version Numbers 1 and 2 are reserved for BAI; Version Number 3 indicates BTRS.

## 02 Bank Hdr
02 - GROUP HEADER
FIELD NAME | REQUIRED or OPTIONAL | DESCRIPTION | BTRS vs. BAI
Record Code | Mandatory | 02 | N/C
Ultimate Receiver ID | Optional | Final receiver of this group of data | N/C
Originator ID | Mandatory | Originator; alphanumeric | N/C
Group Status | Mandatory | Status (i.e., Update, Deletion, etc.) | N/C
As-of Date | Mandatory | Originator date; YYMMDD format | N/C
As-of Time | Optional | Originator's local time; Military format (2400) | See Notes below
Currency Code | n/a | null | See Notes below
As-of Date Modifier | Optional | Indicator for the type of information being reported (previous day or same-day) | See Notes below
End of Record Delimiter | Mandatory | / | N/C
N/C = No change from BAI 2 format
| SAMPLE 02 RECORD: | 02,031001234,122099999,1,040620,2359,2,USD,2/
FIELD | NOTES
Military Time | For the purpose of Information Reporting, the general guideline is that 0000 indicates the beginning of the day and 2400 indicates the end of the day for the date indicated. However 0000 and 2400 both represent "midnight" in military format, the usage varying by organizations and applications. To avoid confusion and minimize conflicts with downstream applications, the best practice is to avoid 2400 and use a time range of 0000 - 2359.
Currency Code | In BAI this field was Optional and defaulted to USD. In BTRS the field is not used in Record 02. The Currency Code is only required at the account level in Record 03 since a single bank may report accounts with different currencies. In Record 02, no value is reported but the comma delimiter is still required to maintain the placeholder for the field.
As-of Date Modifier | In BAI this field was Optional and used for reference only; in BTRS the field is Mandatory. The BAI field designator of 1 for "Interim Previous Day Data" has been retired and should not be used.

## 03 Account Hdr
03 - ACCOUNT IDENTIFIER AND SUMMARY STATUS
FIELD NAME | REQUIRED or OPTIONAL | DESCRIPTION | BTRS vs. BAI
Record Code | Mandatory | 03 | N/C
Customer Account Number | Mandatory | Customer account number at originator financial institution; alphanumeric | N/C
Currency Code | Mandatory | Currency of the account being reported as defined in ISO 4217 | See Notes below
Type Code | Conditional | Identifies the type of Summary or Status data being reported | See Notes below
Amount | Conditional | Amount of item reported with preceding Type Code; Currency Code determines the implied decimal | See Notes below
Item Count | Conditional | Integer field; for Summary Type Codes only | N/C
Funds Type | Conditional | Float type indicator | See Notes below
End of Record Delimiter | Mandatory | / | N/C
N/C = No change from BAI 2 format
| SAMPLE 03 RECORDS: | 03,1111111,USD,,,,/
03,2222222,USD,010,500000,,/
03,3333333,USD,010,142606644,,,015,143832007,,,040,142606644,,/
88,045,143817107,,,072,12600,,,074,2300,,,100,12503104,9,,400,11277741,36,/
FIELD | NOTES
Currency Code | In BAI this field was Optional and defaulted to USD. In BTRS the field is Mandatory and based on international standard ISO 4217. The Currency Codes are the same as those used by SWIFT.
Type Code | Many BAI2 Type Codes have been retired and are no longer used in BTRS; refer to the" X9.121 BTRS Version 3 Codes List" available on the X9.org site for a detailed list of viable BTRS Type Codes. Detail Type Codes are mapped to specific Summary Type Codes. If Summary Codes are included, they must correspond to the correct Detail Type Codes.
Amount | In BAI this field was Optional, depending on the specific Type Code reported. Similarly in BTRS, this field is Conditional and dependent on the preceding Type Code. Including a Status or Summary Type Code with no Amount indicates that no amount is being reported (a special case that is different from reporting a zero amount).
Funds Type | Funds Type "D" (Distributed Availability) is not used in BTRS.

## 16 Transaction Detail
16 - TRANSACTION DETAIL RECORD
FIELD NAME | REQUIRED or OPTIONAL | DESCRIPTION | BTRS vs. BAI
Record Code | Mandatory | 16 | N/C
Type Code | Mandatory | Identifies the type of Detail data being reported | See Notes below
Amount | Mandatory | Amount of item reported with previous Type Code; Currency Code determines the implied decimal | N/C
Funds Type | Mandatory | Float type indicator | See Notes below
Bank Reference Number | Conditional | Alphanumeric field defined by the originator | N/C
Customer Reference Number | Conditional | Alphanumeric field defined by the originator | N/C; See Notes below
Text | Conditional | Alphanumeric field defined by the originator | N/C
End of Record Delimiter | Conditional | / | N/C
N/C = No change from BAI 2 format
| SAMPLE 16 RECORD: | 16,165,1500000,1,DD1620,,DEALER PAYMENTS
16,184,150000,S,0,127500,22500,7676166388,/
FIELD | NOTES
Type Code | Many BAI2 Type Codes have been retired and are no longer used in BTRS; refer to the" X9.121 BTRS Version 3 Codes List" available on the X9.org site for a detailed list of viable BTRS Type Codes.
Funds Type | Funds Type "D" (Distributed Availability) is not used in BTRS. In BAI the Funds Type is Optional in Record 16. In BTRS the field is only optional for Detail Type Code 890, which is used for non-monetary information.
Text | Refer to complete ANSI X9.121 documentation for instructions on reporting Fedwire/CHIPS Wire Remittance Information in the BTRS 88 Record.
Language | Characters must apply the UTF-8/Multi-byte format to allow for single byte and double byte character sets.

## 88 Continuation
88 - CONTINUATION RECORD
FIELD NAME | REQUIRED or OPTIONAL | DESCRIPTION | BTRS vs. BAI
Record Code | Mandatory | 88 | N/C
(Next Field) | Mandatory | Continuation of the preceding record | N/C; See Notes Below regarding Fed/CHIPS CTP formats
N/C = No change from BAI 2 format
| SAMPLE 16 RECORD: | 16,115,10000000,S,5000000,4000000,1000000/
88,AX13612,B096132,AMALGAMATED CORP. LOCKBOX
88,DEPOSIT-MISC. RECEIVABLES
FIELD | NOTES
(Next Field) | Refer to complete ANSI X9.121 documentation for instructions on reporting Fedwire/CHIPS Wire Remittance Information in the BTRS 88 Record.
Language | Characters must apply the UTF-8/Multi-byte format to allow for single byte and double byte character sets.

## 49 Account Trailer
49 - ACCOUNT TRAILER
FIELD NAME | REQUIRED or OPTIONAL | DESCRIPTION | BTRS vs. BAI
Record Code | Mandatory | 49 | N/C
Account Control Total | Mandatory | The sum of all the Amount fields reported for this account | N/C
Number of Records | Mandatory | Total number of records in the account, including the 03 Record and this 49 Record and all records in between | N/C
End of Record Delimiter | Mandatory | / | N/C
N/C = No change from BAI 2 format
| SAMPLE 49 RECORD: | 49,18650000,3/

## 98 Bank Trailer
98 - GROUP TRAILER
FIELD NAME | REQUIRED or OPTIONAL | DESCRIPTION | BTRS vs. BAI
Record Code | Mandatory | 98 | N/C
Group Control Total | Mandatory | The sum of all the Account Control Totals reported in the preceding 49 Records | N/C
Number of Accounts | Mandatory | The number of 03 Records in this Group | N/C
Number of Records | Mandatory | Total number of records in the group, including the 02 Record and this 98 Record and all records in between | N/C
End of Record Delimiter | Mandatory | / | N/C
N/C = No change from BAI 2 format
| SAMPLE 98 RECORD: | 98,11800000,2,6/

## 99 File Trailer
99 - FILE TRAILER
FIELD NAME | REQUIRED or OPTIONAL | DESCRIPTION | BTRS vs. BAI
Record Code | Mandatory | 99 | N/C
File Control Total | Mandatory | The sum of all the Group Control Totals reported in the preceding 98 Records | N/C
Number of Groups | Mandatory | The number of 02 Records in the File | N/C
Number of Records | Mandatory | Total number of records in the file, including the 01 Record and this 99 Record and all records in between | N/C
End of Record Delimiter | Mandatory | / | N/C
N/C = No change from BAI 2 format
| SAMPLE 99 RECORD: | 99,1215450000,4,36/

## File Layout
| File Header | Record 01
# | Field Name | Status | Length | Type | Value or Format
1 | Record Code | M | 2 | Numeric, with leading zeros | 01
2 | Sender Identification | M | 1-20 | Alphanumeric | Variable Length
3 | Receiver Identification | M | 1-20 | Alphanumeric | Variable Length
4 | File Creation Date | M | 6 | Numeric | YYMMDD
5 | File Creation Time | M | 4 | Numeric, with leading zeros | HHMM
6 | File Identification Number | M | 1-20 | Numeric
7 | Physical Record Length | O | 1-3 | Numeric, without leading zeros | Military 24 Hour Clock (0000 through 2359)
8 | Block Size | O | 1-3 | Numeric, without leading zeros | Variable Length
9 | Version Number | M | 1-2 | Numeric, without leading zeros | 40-999
10 | End of Record Delimiter | M | 1 | Character | /
| Bank Header | Record 02
# | Field Name | Status | Length | Type | Value or Format
1 | Record Code | M | 2 | Numeric, with leading zeros | 02
2 | Ultimate Receiver Identification | M | 1-20 | Alphanumeric | Variable Length
3 | Bank Identification | M | 1-20 | Alphanumeric | Variable Length
4 | Group Status | M | 1 | Numeric (Integer) | 1 = Update
5 | As-of-Date | M | 6 | Numeric (Integer) | YYMMDD
6 | As-of-Time | O | 4 | Numeric, with leading zeros | HHMM Military 24 Hour Clock (0000 through 2359)
7 | Currency Code | n/a | 0 | (No Longer used) | Null
8 | As-of-Date Modifier | M | 1 | Numeric (Integer) | 2 = Final Previous-day 3 = Interim Same-day 4 = Final Same-day
9 | End of Record Delimiter | M | 1 | Character | /
| Account Header | Record 03
# | Field Name | Status | Length | Type | Value or Format
1 | Record Code | M | 2 | Numeric, with leading zeros | 03
2 | Customer Account Number | M | 1-35 | Can contain alphabetic, numeric, and special characters (except delimiters) | Variable-length field. Accounts may be transmitted with or without leading zeros
3 | Currency Code | M | 3 | Alphabetic | XXX
# | Status Code Format
4 | Type Code | C | 3 | Numeric (Integer) | See "BTRS Status Codes" tab Expressed with leading zeros
5 | Amount | M | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
6 | Item Count | n/a | n/a | n/a | n/a
7 | Funds Type | n/a | n/a | n/a | n/a
# | Summary Code Format
4 | Type Code | O | 3 | Numeric (Integer) | See "BTRS Summary Codes" Spreadsheet
5 | Amount | O | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
6 | Item Count | O | U | Numeric (Integer) | Does not include periods or commas.
7 | Funds Type | O | 1 | Alphanumeric | 0 = immediate availability 1 = one-day availability 2 = two-or-more-days availability S = distributed availability V = value dated Z = unknown (default)
# | The next 3 Fields are Mandatory only on the Condition that Funds Type = S
8 | Immediate Availability | C | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
9 | 1 Day Availability | C | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
10 | 2+ Day Availability | C | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
# | The next 2 are Mandatory only on the Condition that Funds Type = V
8 | Value Date | C | 6 | Numeric (Integer) | YYMMDD
9 | Value Time | C | 4 | Numeric, with leading zeros | HHMM Military 24 Hour Clock (0000 through 2359)
| Transaction Detail | Record 16
# | Field Name | Status | Length | Type | Value or Format
1 | Record Code | M | 2 | Numeric (Integer) | 16
2 | Detail Type Code | M | 3 | Numeric (Integer) | See "BTRS Details Codes" Spreadsheet
3 | Amount | M | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
4 | Funds Type | M | 1 | Alphanumeric | Z = unknown 0 = immediate availability 1 = one-day availability 2 = two-or-more-days availability S = distributed availability V = value dated
# | The next 3 Fields are Mandatory only on the Condition that Funds Type = S
5 | Immediate Availability | C | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
6 | 1 Day Availability | C | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
7 | 2+ Day Availability | C | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
# | The next 2 are Mandatory only on the Condition that Funds Type = V
5 | Value Date | C | 6 | Numeric (Integer) | YYMMDD
6 | Value Time | C | 4 | Numeric, with leading zeros | HHMM Military 24 Hour Clock (0000 through 2359)
# | The next 3 are Optional. The field placement is dependent upon the Funds Type value
5, 7 ,8 | Bank Reference Number 5 (for Funds Type Z/0/1/2) 8 (for Funds Type S) 7 (for Funds Type V) | O | 0-16 ISO & MT | Alphanumeric
6, 9, 8 | Customer Reference Number 6 (for Funds Type Z/0/1/2) 9 (for Funds Type S) 8 (for Funds Type V) | O | 0-16 ISO & MT | Alphanumeric
7, 10, 9 | Text 7 (for Funds Type Z/0/1/2) 10 (for Funds Type S) 9 (for Funds Type V) | O | U | Alphanumeric | Characters within Text shall apply the UTF8/Multi-byte format to allow for single byte and double byte character sets
| Account Trailer | Record 49
# | Field Name | Status | Length | Type | Value or Format
1 | Record Code | M | 2 | Numeric (Integer) | 49
2 | Account Control Total | M | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
3 | Number of Records | M | U | Numeric (Integer) | Does not include periods or commas. Can be signed positive “+”.
4 | End of Record Delimiter | M | 1 | Character | /
| Bank Trailer | Record 98
# | Field Name | Status | Length | Type | Value or Format
1 | Record Code | M | 2 | Numeric (Integer) | 98
2 | Group Control Total | M | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
3 | Number of Accounts | M | 1-3 | Numeric (Integer) | Does not include periods or commas. Can be signed positive “+”.
4 | Number of Records | M | 1-9 | Numeric (Integer) | Does not include periods or commas. Can be signed positive “+”.
5 | End of Record Delimiter | M | 1 | Character | /
| File Trailer | Record 99
# | Field Name | Status | Length | Type | Value or Format
1 | Record Code | M | 2 | Numeric (Integer) | 99
2 | File Control Total | M | 1-23 If not signed 1-24 if signed | Numeric (Integer) | Expressed without a decimal Does not include periods or commas. Can be signed positive “+” or negative “-”.
3 | Number of Banks | M | 1-3 | Numeric (Integer) | Does not include periods or commas. Can be signed positive “+”.
4 | Number of Records | M | 1-9 | Numeric (Integer) | Does not include periods or commas. Can be signed positive “+”.
5 | End of Record Delimiter | M | 1 | Character | /

## File Diagram
01-File Header
Sender ID | Receiver ID | File Creation Date | File Creation Time | File ID # | Physical Record Length | Block Size | Version #
Alphanumeric | Alphanumeric | YYMMDD | 2400 | Numeric | Optional | Optional | 3
02-Bank Header
Ultimate Receiver ID | Originator ID | Group Status | As-of-Date | As-of-Time | Currency Code | As-of-Date Modifier | Repeat for each Bank
Alphanumeric | Alphanumeric | 1=Update | YYMMDD | Optional | No Longer Used | Integer
|  |  |  | 2359 | Always 'Null' | 2=Final Previous-day data
3=Interim Same-day data
4=Final Same-day data
03-Account Header
Customer Acct # | Currency Code | Type Code | Amount | Item Count | Funds Type | Repeat for each Account
Alphanumeric | Alphanumeric
Status Code Format: |  | Conditional | Mandatory | Not Used | Not Used | Repeat for each Code
|  | 010-099 | Default is unsigned
Summary Code Format: |  | Optional | Mandatory | Optional | Optional | Repeat for each Code
|  | 100-699, 900-999 | Default is unsigned | Integer | 0=Immediate Availability
1=One-day Availability
2=Two-day Availability
[5 empty] | S=Distributed Availability | Immediate Amount | 1 Day Amount | 2+ Day Amount
[5 empty] | V=Value dated | Value Date | Value time
Z=Unknown (Default)
16-Transaction Detail
Type Code | Amount | Funds Type |  |  |  | Bank Reference # | Cust. Reference # | Text | Repeat for each Code
100-699, 900-999 | Integer | Alphanumeric |  |  |  | Optional | Optional | Optional
| Without decimal | 0=Immediate Availability |  |  |  | Alphanumeric | Alphanumeric | Alphanumeric
1=One-day Availability
2=Two-day Availability
|  | S=Distributed Availability | Immediate Amount | 1 Day Amount | 2+ Day Amount
|  | V=Value dated | Value Date | Value time
Z=Unknown (Default)
88-Continuation Record
Continuation of last field used
49-Account Trailer
Acct. Control Total | # of Records
Sum of Amount Fields | Integer
98-Bank Trailer
Group Control Total | # of Accounts | # of Records
Sum of Account Fields | Integer | Integer
99-File Trailer
File Control Total | # of Groups | # of Records
Sum of all Fields | Integer | Integer